## February 2026
WEEKLY VIEW
|  | WEEK-1 | [6 empty] | WEEK-2 | [6 empty] | WEEK-3
TASK | DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Week 1 Deliverables | 7
Role-Based Access Control Design | 2 | bar: WEEK-1 1 to WEEK-1 2
Admin Database Schema Design | 2 | bar: WEEK-1 3 to WEEK-1 4
Admin Dashboard Component | 3 | bar: WEEK-1 5 to WEEK-1 7
Week 2 Deliverables | 7
Admin Users Management View | 3 | bar: WEEK-2 1 to WEEK-2 3
Admin Restaurants Verification | 2 | bar: WEEK-2 4 to WEEK-2 5
Admin Orders Viewing System | 2 | bar: WEEK-2 6 to WEEK-2 7
Week 3 Deliverables | 7
Admin Delivery Partners Tracking | 3 | bar: WEEK-3 1 to WEEK-3 3
Admin Settings Configurations | 2 | bar: WEEK-3 4 to WEEK-3 5
Backend admin.routes.js | 2 | bar: WEEK-3 6 to WEEK-3 7