## January 2026
Task | Days | Week 1 (1-6) | [5 empty] | Week 2 (1-6) | [5 empty] | Week 3 (1-6) | [5 empty] | Week 4 (1-6)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6
Problem Identification | 2 | bar: Week 1 (1-6) 1 to Week 1 (1-6) 2
Requirement Gathering | 2 | bar: Week 1 (1-6) 3 to Week 1 (1-6) 4
Literature Review | 2 | bar: Week 1 (1-6) 5 to Week 1 (1-6) 6
System Design Discussion | 3 | bar: Week 2 (1-6) 1 to Week 2 (1-6) 3
Planning & Architecture | 3 | bar: Week 2 (1-6) 4 to Week 2 (1-6) 6
Module Planning | 3 | bar: Week 3 (1-6) 1 to Week 3 (1-6) 3
Initial Development Setup | 3 | bar: Week 3 (1-6) 4 to Week 3 (1-6) 6
Feature Implementation Phase 1 | 4 | bar: Week 4 (1-6) 1 to Week 4 (1-6) 4
Team Review & Adjustments | 2 | bar: Week 4 (1-6) 5 to Week 4 (1-6) 6

## February 2026
Task | Days | Week 1 (1-6) | [5 empty] | Week 2 (1-6) | [5 empty] | Week 3 (1-6) | [5 empty] | Week 4 (1-6)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 | 5 | 6
Backend Setup | 3 | bar: Week 1 (1-6) 1 to Week 1 (1-6) 3
API Endpoint Development | 3 | bar: Week 1 (1-6) 4 to Week 1 (1-6) 6
ML Model Training | 4 | bar: Week 2 (1-6) 1 to Week 2 (1-6) 4
Prediction Logic Development | 2 | bar: Week 2 (1-6) 5 to Week 2 (1-6) 6
Database Integration | 3 | bar: Week 3 (1-6) 1 to Week 3 (1-6) 3
ML Model Testing | 2 | bar: Week 3 (1-6) 4 to Week 3 (1-6) 5
Accuracy Evaluation | 2 | bar: Week 3 (1-6) 6 to Week 4 (1-6) 1
Database Query Optimization | 3 | bar: Week 4 (1-6) 2 to Week 4 (1-6) 4
Backend Logging | 2 | bar: Week 4 (1-6) 5 to Week 4 (1-6) 6